TRUVIS INTERNATIONAL SERVICES

KYC / AML / Onboarding Platform

Development Plan

Claude Code  ·  Supabase  ·  Next.js  ·  Vercel

Purpose: MVP-first implementation roadmap from PRD to executable build

Audience: Lead Developer  ·  Claude Code Sessions  ·  Technical Lead

Version 1.0  ·  2026  ·  Confidential

|  | This plan translates the PRD into a build-ready implementation blueprint. It is intended as the direct input to Claude Code sessions. Each milestone is independently executable. Assumptions are clearly labelled [ASSUMPTION]. Decisions requiring confirmation before coding are labelled [CONFIRM BEFORE BUILD]. |
| --- | --- |

SECTION 01

# Delivery Strategy

The PRD defines a 15-module compliance infrastructure. The delivery strategy below scopes a realistic MVP that satisfies the AML compliance baseline for individual customer onboarding, with a clean architectural foundation for all subsequent phases. Complexity is deferred — not discarded.

## 1.1 MVP Scope — Build Now

|  | [ASSUMPTION] MVP target: single-tenant deployment for internal TruVis use or a single pilot tenant. Multi-tenant generalisation begins in Phase 2 once the data model is proven. |
| --- | --- |

| Module / Feature | PRD Reference | Reason for MVP Inclusion |
| --- | --- | --- |
| M-01 Onboarding Orchestrator — individual flow only | Section 1, 2.1 | Entry point for all compliance. Without it nothing works. |
| M-02 Individual KYC — data collection + document upload | Section 2.1, 4.1 | Core compliance obligation for natural persons. |
| M-09 Document Management — upload, store, signed URL retrieval | Section 4.1 | Required by KYC. Storage infra needed before anything else. |
| M-07 Screening — OFAC/UN/EU sanctions + PEP (Tier 1) | Section 2.1, 3.4 | AML legal obligation. Cannot onboard without screening. |
| M-08 Risk Scoring — 3-dimension basic score (customer, geo, product) | Section 4.3 | Required to route to CDD vs EDD vs auto-approve. |
| M-10 Case Management — basic queue, analyst review, RAI, decision | Section 2.4, 3.5 | Required for human review when auto-approval not triggered. |
| M-11 Approval Workflow — single-stage sequential | Section 2.3 | Required to record compliance decisions. |
| M-12 Audit Trail — append-only event log | Section 4.4 | Regulatory obligation from day one. Must be built first. |
| M-13 Consent — capture at session start, legal basis, purpose | Section 3.6 | PDPL/DPR obligation. Required before any PII collection. |
| Auth + RBAC — Tenant Admin, MLRO, Analyst, Read-Only | Section 5.3 | Cannot run a review queue without role-based access. |
| M-15 Admin Config — minimal: tenant settings, flow activation | Section 8 | Enough config to operate without code changes per tenant. |

## 1.2 Phase 2 — Build Next (Months 5–8)

| Module / Feature | PRD Reference | Trigger for Inclusion |
| --- | --- | --- |
| M-03/M-04 Corporate KYB + UBO Engine | Section 2.2, 4.2 | First corporate client or tenant requiring KYB. |
| M-05/M-06 CDD/EDD differentiation — full EDD form | Section 2.3 | Once risk routing is proven, formalise EDD data collection. |
| M-08 Risk Scoring — full 5-dimension with configurable weights | Section 4.3 | After MVP risk model is calibrated in production. |
| M-14 Ongoing Monitoring — periodic review, document expiry alerts | Section 3.6 | After first onboarded customers reach review cycle. |
| M-07 Screening — adverse media, custom watchlists, batch re-screening | Section 3.4 | After initial list screening is proven stable. |
| M-11 Approval Workflow — multi-stage, parallel approval paths | Section 3.5 | When MLRO sign-off on EDD requires dual approval. |
| M-15 Admin Config — workflow builder (form + step config) | Section 8.2 | When second tenant or second product type is onboarded. |
| Multi-language UI (Arabic primary) | Section 8.3 | UAE market rollout. |
| Multi-tenant full isolation (schema separation) | Section 5.2 | Second commercial tenant. |
| Embeddable SDK / headless API mode | Section 3.1 | Partner or white-label integration. |

## 1.3 Phase 3 — Enterprise (Months 9–12)

| Visual drag-and-drop workflow builder | M-15 full feature. JSON schema is built in Phase 2; visual builder is the UI layer on top. |
| --- | --- |
| ML-assisted risk scoring calibration | Requires production data volume to train. Cannot be built speculatively. |
| Video KYC integration | Regulatory pre-approval required in most jurisdictions before building. |
| Blockchain/VASP address screening | Specialist integration. Phase 3 for crypto-vertical tenants. |
| Registry API integrations (ADGM, DIFC portals) | API availability and authentication must be confirmed with each authority. |
| Advanced analytics — analyst productivity, SLA compliance | Requires Phase 2 operational data before metrics are meaningful. |
| Mobile SDK (React Native) | Phase 3. Web-first for MVP and Phase 2. |
| Data subject rights automation (access/erasure requests) | Partial manual process acceptable in MVP. Automation in Phase 3. |

## 1.4 Explicitly NOT Built in Version 1

|  | The following must not be built in MVP even if technically feasible. They introduce complexity that will block delivery of the compliance baseline. |
| --- | --- |

| Full no-code workflow builder UI | Build JSON-defined workflows first. Visual builder is Phase 3. |
| --- | --- |
| Corporate KYB / UBO recursive resolution | Separate complex module. Individual KYC is the foundation. |
| SAR/STR filing integration (goAML) | MLRO handles filing manually in MVP. Integration is Phase 2. |
| Video KYC | Regulatory approval needed. Not in MVP. |
| Complete data subject rights automation | Manual process documented; automation deferred. |
| Financial transaction monitoring | Outside MVP scope. Separate system or Phase 3+. |
| Open banking / PSD2 integration | Not required for UAE MVP. |
| Blockchain screening (Chainalysis/Elliptic) | Crypto vertical is Phase 3. |
| Multi-region data residency enforcement | Single UAE region for MVP. KSA data residency in Phase 2. |

SECTION 02

# System Architecture

## 2.1 Architecture Overview

The stack is Next.js 14 (App Router) on Vercel for frontend and API layer, Supabase for Postgres, Auth, Storage, and Edge Functions, with an adapter layer for all third-party integrations. The architecture is deliberately monorepo-first for MVP, structured for microservice extraction in Phase 2.

|  | [ASSUMPTION] Next.js App Router with React Server Components. API routes used for mutation and integration endpoints. No separate Express/Fastify server in MVP — Vercel serverless functions are sufficient for MVP load. |
| --- | --- |

## 2.2 Layer Responsibilities

| Layer | Technology | Responsibilities |
| --- | --- | --- |
| Frontend — App Shell | Next.js 14 App Router, Tailwind CSS, shadcn/ui | Onboarding journey UI, case management interface, admin config UI, analyst workbench, consent screens. All UI state managed in React. Server Components for read-heavy views. |
| API Layer | Next.js API Routes (Route Handlers) on Vercel | All mutation endpoints (start session, submit KYC data, upload document trigger, record decision). Thin orchestration layer — no business logic. Calls Supabase directly or delegates to Edge Functions. |
| Serverless / Heavy Processing | Supabase Edge Functions (Deno) | Screening calls (async), risk score computation, webhook delivery, document hash computation, audit event emission, external IDV provider callbacks. Long-running or latency-sensitive work that should not block the API layer. |
| Database | Supabase Postgres | All structured data. Multi-tenant with tenant_id on all rows. RLS enforced at DB layer. Audit log as append-only table. Workflow config as JSONB. RPC functions for complex multi-step operations. |
| Storage | Supabase Storage | All uploaded documents (passports, IDs, proof of address). Bucket-per-tenant. Signed URLs only — no public access. Encrypted at rest (Supabase default AES-256). |
| Auth | Supabase Auth | User authentication (email+password + MFA). JWT with custom claims for tenant_id, role, and permissions. RLS policies use auth.uid() and auth.jwt() claims. |
| Background Jobs | Supabase Edge Functions + pg_cron | Periodic review scheduling, document expiry checks, batch screening re-runs, retention policy enforcement. pg_cron for scheduled triggers. |
| CDN / Edge | Vercel Edge Network | Static asset delivery, ISR for non-PII public pages, Edge Middleware for auth guard and tenant routing. |

## 2.3 What Should NOT Live Only in Vercel Serverless Functions

|  | Vercel serverless functions have cold start latency, 10s default timeout (60s max on Pro), and no persistent connections. The following must NOT be architected to rely solely on Vercel functions. |
| --- | --- |

| Long-running external IDV provider calls | IDV providers (Sumsub, Onfido) use async webhook callbacks, not synchronous responses. Initiation in API route, result received in Supabase Edge Function via webhook. |
| --- | --- |
| Screening provider API calls | Async. Submit screening job in API route. Result returned via webhook to Edge Function. Do not attempt synchronous screening in a Vercel function. |
| Audit trail writes from multiple events | Audit writes happen via Postgres triggers and Edge Functions — not via API routes that can time out mid-transaction. |
| Document processing (hash, virus scan, metadata extract) | CPU-intensive. Handled in Supabase Edge Function triggered by Storage event, not in Vercel. |
| Batch re-screening jobs | pg_cron scheduled job triggers Edge Function. Never a Vercel cron for compliance-critical operations — too unreliable. |

## 2.4 Module Boundary Design for Extensibility

Each PRD module maps to a bounded context within the codebase. Module boundaries are enforced by directory structure and explicit import rules. Phase 2 modules (KYB, UBO) can be added as new bounded contexts without touching MVP module internals.

SECTION 03

# Database and Data Model Plan

## 3.1 Multi-Tenant Design Approach

All tenant data lives in a single Postgres schema (public) with tenant_id UUID as a mandatory column on every table. Row Level Security (RLS) enforces tenant isolation at the database layer. This is the correct choice for MVP scale — schema-per-tenant is a Phase 2 migration if a single high-volume regulated tenant requires it.

|  | [ASSUMPTION] Shared schema with RLS for MVP. The tenant_id column is non-nullable and indexed on every table. RLS policies reference auth.jwt() ->> 'tenant_id' for all user-facing queries. Platform super-admin role bypasses RLS via a service-role key stored only in Supabase Edge Functions, never exposed to the frontend. |
| --- | --- |

## 3.2 Core Table Inventory — MVP

| Table Name | Purpose | Immutable / Versioned / Mutable | Key Relationships |
| --- | --- | --- | --- |
| tenants | Tenant registry. Configuration reference. | Mutable (settings update). Created record is immutable. | Parent of all data |
| tenant_config | JSONB config per tenant — active modules, risk weights, flow definitions, branding. | Versioned. New row per change. Latest flag. | tenants |
| users | Platform users (analysts, admins, MLRO). Extends Supabase auth.users. | Mutable (status, role changes logged in audit). | tenants, user_roles |
| user_roles | Role assignments per user per tenant. Many-to-many. | Append-only. Revocations create new row with revoked_at. | users, roles |
| roles | Role definitions. Seeded by platform. Tenant cannot create arbitrary roles. | Immutable once created. | — |
| onboarding_sessions | One record per onboarding attempt. Tracks flow state, step progress, status. | Mutable (status, current_step). State machine transitions logged to audit. | tenants, customers |
| customers | Customer master record. Created on session initiation. Status-driven. | Mutable (status, risk_band). All field changes versioned in customer_data_versions. | tenants, onboarding_sessions |
| customer_data_versions | Full snapshot of customer data fields at each change event. Append-only. | Append-only [IMM]. | customers |
| kyc_results | KYC verification outcome per customer per attempt. Stores IDV provider result, scores, pass/fail. | Immutable after creation. | customers |
| documents | Document metadata record (not the file — file in Storage). | Immutable after upload. Status updates append-only. | customers, onboarding_sessions |
| document_events | Append-only log of all document state changes (uploaded, reviewed, accepted, rejected, expired). | Append-only [IMM]. | documents |
| screening_jobs | One record per screening run. Contains list versions, parameters, status. | Immutable after completion. | customers |
| screening_hits | Individual hit records per screening run. One row per match. | Immutable after creation. Resolution recorded in screening_hit_resolutions. | screening_jobs |
| screening_hit_resolutions | Analyst resolution of each hit (true match / false positive). Append-only. | Append-only [IMM]. | screening_hits, users |
| risk_assessments | One record per risk computation. Stores score, band, factor breakdown JSONB, rule_set_version. | Immutable after creation. | customers |
| cases | Case record for manual review. One case per onboarding decision point. | Mutable (status, assignee). All status changes in case_events. | customers, users |
| case_events | Append-only log of all case actions: created, assigned, note added, RAI sent, escalated, decided. | Append-only [IMM]. | cases, users |
| approvals | Approval decision record. One per approval stage per case. | Immutable after decision recorded. | cases, users |
| consent_records | Consent capture at session start. One row per purpose per customer per version. | Immutable. Withdrawal is new row with withdrawn_at. | customers, onboarding_sessions |
| audit_log | Append-only event log for all system events across all modules. | Append-only [IMM]. No UPDATE/DELETE permissions. | All tables |
| workflow_definitions | JSONB workflow definitions per tenant per customer type. Versioned. | Versioned. New row per change. | tenants |

## 3.3 Audit Log Table Design

The audit_log table is the most critical table in the system. It is designed with maximum immutability.

|  | The Postgres role used by the application (anon / authenticated) must have INSERT-only access to audit_log. No UPDATE or DELETE is granted to any application role. Only the service-role (used only in Edge Functions) has INSERT. The table has a Postgres trigger that prevents UPDATE and DELETE at the database level as a secondary control. |
| --- | --- |

| Column | Definition and Constraint |
| --- | --- |
| id | UUID PRIMARY KEY DEFAULT gen_random_uuid() — immutable once set |
| tenant_id | UUID NOT NULL REFERENCES tenants(id) — RLS applied |
| event_time | TIMESTAMPTZ NOT NULL DEFAULT now() — set by DB, not application |
| event_type | TEXT NOT NULL — enum-like: customer.field_changed, document.uploaded, screening.initiated, case.decision_recorded, approval.granted, consent.captured, etc. |
| actor_id | UUID — user ID (NULL for system events) |
| actor_role | TEXT — role at time of action |
| entity_type | TEXT NOT NULL — customers / documents / cases / approvals / etc. |
| entity_id | UUID NOT NULL — the ID of the affected record |
| payload | JSONB NOT NULL — event-specific data. PII stored as tokenised reference, not raw value. |
| session_id | UUID — onboarding session reference if applicable |
| ip_address | INET — masked to /24 for privacy (last octet zeroed) |
| prev_hash | TEXT — SHA-256 hash of previous row in tenant partition (hash chaining). NULL for first row. |
| row_hash | TEXT GENERATED — SHA-256 of (tenant_id ¦¦ event_time ¦¦ event_type ¦¦ entity_id ¦¦ payload::text) |

## 3.4 RLS Strategy

Row Level Security is enabled on every tenant-data table. Policies follow a consistent pattern. The following three policy types cover all cases.

| Policy Type | Pattern | Applied To |
| --- | --- | --- |
| Tenant isolation — all authenticated users | auth.jwt() ->> 'tenant_id' = tenant_id | All data tables. Every table policy starts with this condition. |
| Role-gated read | auth.jwt() ->> 'role' IN ('mlro', 'senior_reviewer', 'analyst') AND tenant_id = ... | cases, screening_hits, risk_assessments — only compliance roles can read. |
| Append-only enforcement | WITH CHECK (true) — SELECT/INSERT allowed. No UPDATE policy created. No DELETE policy created. | audit_log, case_events, document_events, customer_data_versions, consent_records, screening_hits. |
| Service role bypass | Service role key (stored only in Edge Functions env vars) bypasses RLS for system writes (audit log, background jobs). | Edge Functions only. Never exposed to browser or API routes that touch untrusted input. |
| Admin read-all (tenant-scoped) | auth.jwt() ->> 'role' = 'tenant_admin' | All tables within the tenant. Tenant admin cannot read other tenants. |

SECTION 04

# Auth, Permissions, and User Roles

## 4.1 Supabase Auth Implementation

| Authentication method | Email + password with mandatory email verification. MFA (TOTP) enforced for MLRO and Tenant Admin roles. Magic link as secondary option for analyst onboarding. |
| --- | --- |
| JWT custom claims | After sign-in, a Supabase Auth hook (Database Webhook or Edge Function) enriches the JWT with: tenant_id, role, permissions array, mfa_verified flag. Claims are read by RLS policies. |
| Session management | Supabase session with JWT + refresh token. Session TTL: 1 hour access token, 7-day refresh for standard roles. 8-hour access token max for MLRO (compliance review sessions can run long). |
| Tenant association | Users are associated to a tenant at invitation time. The invitation flow creates the user_roles record before the user activates their account. A user cannot self-register without an invitation. |
| Multi-tenant routing | Subdomain-based or path-based tenant routing. Tenant slug resolved from URL at Edge Middleware. tenant_id injected into request context. JWT claim validated against resolved tenant. |

|  | [CONFIRM BEFORE BUILD] MFA enforcement mechanism in Supabase: Supabase Auth supports TOTP MFA. The enforcement of MFA for specific roles requires either: (a) a hook that checks mfa_verified in JWT before allowing access, or (b) middleware that redirects to MFA setup for roles requiring it. Confirm which approach aligns with Supabase's current MFA enforcement hooks before implementation. |
| --- | --- |

## 4.2 RBAC Model

| Role | Tenant Scope | Key Permissions | MFA Required |
| --- | --- | --- | --- |
| Platform Super-Admin | Cross-tenant (platform operator only) | Read tenant config. Manage tenant creation. Access audit log (read-only). Cannot read customer PII. Cannot make compliance decisions. | Yes — mandatory |
| Tenant Admin | Single tenant | Manage users and role assignments. Configure workflow (M-15). View all cases and decisions. Cannot make MLRO-level compliance decisions. | Yes — mandatory |
| MLRO / Compliance Officer | Single tenant | All case access. EDD case review and decision. SAR case access. Audit trail read. Risk scoring configuration. Override capability with logged rationale. | Yes — mandatory |
| Senior Reviewer | Single tenant | Assigned case review. EDD case review (if role-permitted). Approve/reject with rationale. Cannot see SAR case status. | Recommended — configurable per tenant |
| Analyst (Reviewer) | Single tenant | Assigned cases only. Document review. Screening hit resolution. Request Additional Information. Cannot approve high-risk without second reviewer. | No — but session logging required |
| Onboarding Agent | Single tenant | Initiate onboarding session. Assist customer with data entry. Upload documents on customer behalf. Cannot see EDD data. Cannot make decisions. | No |
| Read-Only / Reporting | Single tenant | Aggregate and anonymised reports only. No individual customer PII. No case detail access. | No |

## 4.3 Permissions Enforcement — DB Layer vs App Layer

| Permission Check | Enforced In | Rationale |
| --- | --- | --- |
| Tenant data isolation | Database (RLS) | Must be enforced at DB. App layer bypass is a critical vulnerability. |
| Read access to cases by role | Database (RLS policy) | Role claim in JWT checked in RLS. No SQL query can return another tenant's cases. |
| Audit log immutability | Database (no UPDATE/DELETE grant + trigger) | Cannot be enforced in app layer alone. DB-level protection required. |
| Approve/reject a case | App layer + DB constraint | App layer checks role before presenting action. DB-level CHECK constraint on approvals table ensures decision is by valid role. Both layers. |
| Access to SAR case status | App layer (field-level masking) | SAR flag shown only to MLRO role in UI. DB query returns field but UI masks it for non-MLRO roles. Consider DB-level column-level security in Phase 2. |
| MFA verification before access | Edge Middleware + JWT claim | mfa_verified claim in JWT. Middleware checks before routing to sensitive paths. |
| Document signed URL generation | Supabase Storage RLS + app layer | Only authenticated users of the correct tenant and role can call the signed URL generation endpoint. Storage bucket RLS enforces tenant. |
| Admin config write (workflow changes) | App layer + DB RLS | Only tenant_admin role can write to tenant_config and workflow_definitions. Enforced in both RLS policy and API route role check. |

SECTION 05

# Workflow and Configuration Architecture

## 5.1 Onboarding Workflow Engine — MVP Approach

For MVP, the workflow engine is a JSON-defined state machine implemented in the application layer. It is not a visual builder — that is Phase 3. The workflow definition is a JSONB document stored in the workflow_definitions table, versioned per tenant and customer type.

|  | [ASSUMPTION] The MVP workflow engine is a TypeScript state machine that reads a workflow_definition JSON and executes steps sequentially. Conditional branching is supported via a simple if/then rule evaluated against session data. This is sufficient for individual KYC. The complexity of a full rules engine (M-15 Phase 3) is not needed in MVP. |
| --- | --- |

### 5.1.1 Workflow Definition Schema (MVP)

Each workflow definition follows this structure, stored as JSONB in workflow_definitions:

|  | { "id": "individual-kyc-standard-v1", "version": 1, "customer_type": "individual", "jurisdiction": "UAE", "steps": [ { "id": "consent", "type": "consent", "required": true, "config": { "purposes": ["kyc", "aml", "data_processing"], "notice_version": "1.0" } }, { "id": "personal-data", "type": "form", "required": true, "fields": ["full_name", "dob", "nationality", "address", "occupation", "source_of_funds"], "next": "document-upload" }, { "id": "document-upload", "type": "document", "required": true, "config": { "primary": ["passport", "national_id"], "secondary": ["proof_of_address"] }, "next": "screening" }, { "id": "screening", "type": "automated", "action": "run_screening", "next": "risk-score" }, { "id": "risk-score", "type": "automated", "action": "compute_risk", "branches": [ { "condition": "risk_band == LOW", "next": "auto-approve" }, { "condition": "risk_band == MEDIUM", "next": "standard-review" }, { "condition": "risk_band == HIGH", "next": "edd-review" }, { "condition": "risk_band == UNACCEPTABLE", "next": "senior-escalation" } ] } ] } |
| --- | --- |

### 5.1.2 Workflow Engine Implementation

The engine is a TypeScript class (WorkflowEngine) that lives in /modules/onboarding/engine.ts. It is called from API routes and Edge Functions. Key methods:

| WorkflowEngine.loadDefinition(tenant_id, customer_type) | Reads latest active workflow_definition from Supabase for the tenant/type. Returns typed WorkflowDefinition object. |
| --- | --- |
| WorkflowEngine.getCurrentStep(session_id) | Returns the current step definition for an in-progress session. Reads from onboarding_sessions.current_step_id. |
| WorkflowEngine.advance(session_id, step_result) | Validates step completion, evaluates branch conditions against session data and step_result, determines next step, updates onboarding_sessions, writes audit event. |
| WorkflowEngine.evaluateBranch(conditions, session_data) | Pure function. Evaluates condition string against session data object. Returns matching branch or throws if no branch matches. |
| WorkflowEngine.getCompletionStatus(session_id) | Returns whether all required steps are complete and what the final routing decision is. |

## 5.2 Admin Config Layer — MVP

In MVP, admin configuration is a structured settings UI — not a drag-and-drop builder. The following settings are configurable via the Tenant Admin interface without code changes.

| Config Category | Configurable In MVP | Phase for Full Builder |
| --- | --- | --- |
| Active modules | Toggle on/off per module (which flow steps are enabled) | N/A — always admin-configurable |
| Risk score thresholds | Numeric inputs for band boundaries (Low/Medium/High/Unacceptable cutoffs) | Phase 2 (weight per dimension) |
| Document requirements | Select accepted document types per customer type from a predefined list | Phase 2 (custom document types) |
| Approval routing | Select role required per approval stage from dropdown | Phase 2 (multi-stage builder) |
| Notification templates | Edit copy for system-generated emails/notifications. Cannot disable mandatory notifications. | Phase 2 (full template builder) |
| Branding | Logo upload, primary colour, company name — applied to customer-facing UI | MVP — straightforward |
| Workflow activation | Toggle between workflow versions. Cannot activate without MLRO acknowledgement checkbox. | MVP (toggle only) |
| Risk weight overrides | Not configurable in MVP — weights are hardcoded per PRD defaults. | Phase 2 |

## 5.3 Extensibility Design Decisions

| JSONB workflow definitions from day one | Even though the UI is a simple toggle in MVP, store workflow definitions as JSONB. This means the Phase 3 visual builder simply writes JSONB — it does not require a data model change. |
| --- | --- |
| Step type enum | Define all possible step types (form, document, automated, consent, decision, notification) as an enum in the schema now. Adding new step types in Phase 2 is additive — no breaking change. |
| Rule condition syntax fixed at MVP | The simple "field operator value" condition syntax defined in MVP becomes the foundation of the Phase 3 rules engine. Do not invent ad-hoc condition syntax — define the canonical format now. |
| Module registry | A modules table in the DB lists all available modules with their status (active/inactive) per tenant. Adding Phase 2 modules is a DB insert + new directory — not a schema change. |
| Workflow versioning from day one | Every workflow_definition change creates a new version row. The version applied at the start of each onboarding session is stored with the session. Historic sessions always replay against the workflow version active when they started. |

SECTION 06

# API and Integrations Plan

## 6.1 MVP Internal API Surface

All API routes are Next.js Route Handlers under /app/api/. Each route is thin: auth check, role check, input validation (Zod), delegate to module service, return typed response. No business logic in route handlers.

| Route | Method | Module | Notes |
| --- | --- | --- | --- |
| /api/sessions | POST | Onboarding | Initiate session. Returns session_id and first step definition. |
| /api/sessions/[id] | GET | Onboarding | Get session state and current step. |
| /api/sessions/[id]/steps/[stepId] | POST | Onboarding | Submit step completion. Advances workflow. Returns next step. |
| /api/customers/[id] | GET | KYC | Get customer record with current KYC status. |
| /api/customers/[id]/data | PATCH | KYC | Update customer field data. Creates new customer_data_version row. |
| /api/documents/upload-url | POST | Documents | Generate signed upload URL for direct-to-Supabase-Storage upload. Returns signed URL + document_id. |
| /api/documents/[id] | GET | Documents | Get document metadata and generate signed download URL (15-min TTL). |
| /api/screening/[customerId] | POST | Screening | Initiate screening job. Async — returns job_id. Result delivered via Edge Function on webhook. |
| /api/screening/jobs/[jobId] | GET | Screening | Poll screening job status and results. |
| /api/screening/hits/[hitId]/resolve | POST | Screening | Record analyst resolution of a screening hit. |
| /api/risk/[customerId] | POST | Risk | Trigger risk score computation. Returns assessment_id. |
| /api/risk/[customerId]/latest | GET | Risk | Get latest risk assessment with factor breakdown. |
| /api/cases | GET | Cases | List cases for current user (role-filtered). Supports status, assigned_to filters. |
| /api/cases/[id] | GET | Cases | Get full case record with all associated data. |
| /api/cases/[id]/events | POST | Cases | Add case event (note, RAI, escalation). Append-only. |
| /api/approvals/[caseId] | POST | Approvals | Record approval decision for a case stage. |
| /api/consent | POST | Consent | Capture consent record at session start. |
| /api/consent/[customerId] | GET | Consent | Get consent status for a customer. |
| /api/audit | GET | Audit | Query audit log (MLRO/Admin only). Filtered by entity_type, entity_id, date range. |
| /api/admin/config | GET/PATCH | Admin | Get/update tenant configuration. Tenant Admin role only. |
| /api/admin/workflows | GET/POST | Admin | List workflow definitions. Create new version. |
| /api/webhooks/idv | POST | KYC | Inbound webhook from IDV provider. Validated by signature. Triggers Edge Function. |
| /api/webhooks/screening | POST | Screening | Inbound webhook from screening provider. Triggers Edge Function. |

## 6.2 External Provider Adapter Pattern

All third-party integrations use an adapter interface. Changing provider requires only a new adapter implementation — no changes to module business logic. This is critical for screening (provider lock-in risk) and IDV (cost and quality vary by market).

|  | // Example — Screening Adapter Interface (TypeScript) interface ScreeningAdapter { submitScreening(params: ScreeningParams): Promise<{ job_id: string }>; getResults(job_id: string): Promise<ScreeningResult>; parseWebhook(body: unknown, signature: string): Promise<ScreeningResult>; } // Concrete implementations: // ComplyAdvantageAdapter implements ScreeningAdapter // WorldCheckAdapter implements ScreeningAdapter // MockScreeningAdapter implements ScreeningAdapter ← used in dev/test // Injected via factory based on tenant config: const adapter = ScreeningAdapterFactory.create(tenant.screening_provider); |
| --- | --- |

## 6.3 Essential MVP External Integrations

| Integration | Provider Options (start with) | Integration Pattern | MVP / Phase |
| --- | --- | --- | --- |
| Identity Verification (IDV) | Sumsub (recommended for GCC/CIS) or Onfido. Start with ONE provider. | Async: initiate via API → receive result via webhook → Edge Function processes → updates kyc_results. | MVP — essential |
| Sanctions + PEP Screening | ComplyAdvantage (recommended: real-time API + webhook, GCC-aware). | Async: submit job → webhook result → Edge Function → updates screening_jobs/hits. | MVP — essential |
| Email Notifications | Resend (recommended: excellent Next.js integration) or AWS SES. | Synchronous call from Edge Function. Fire-and-forget with error logging. | MVP — essential |
| SMS / WhatsApp | Twilio SMS for MVP. WhatsApp Business API for Phase 2 (UAE primary channel). | Synchronous from Edge Function. OTP delivery for email/phone verification. | MVP (SMS) / Phase 2 (WhatsApp) |
| E-Signature / Consent | Native in MVP — custom consent capture form with legal text + IP/timestamp logging. DocuSign for Phase 2 where wet-signature equivalent is required. | Synchronous. Consent record written to consent_records table. | MVP (native) / Phase 2 (DocuSign) |
| Address Verification | Google Maps Geocoding API for address autocomplete and validation. | Synchronous API call from frontend on address field blur. | MVP — recommended, not essential |

## 6.4 Webhook Handling Architecture

Inbound webhooks from IDV and screening providers must be handled reliably. The following pattern avoids dropped events and timeout failures.

| Step 1 — Receive and acknowledge | Vercel API route /api/webhooks/[provider] receives the POST. Validates HMAC signature immediately. Returns 200 within 3 seconds (before any processing). This prevents provider retry floods. |
| --- | --- |
| Step 2 — Write to queue | The validated raw webhook body is written to a webhook_events table in Supabase (tenant_id, provider, payload JSONB, status: pending, received_at). |
| Step 3 — Edge Function processes | A Supabase Edge Function is triggered by the Postgres insert (via pg_net or Database Webhook). It processes the webhook payload, updates the relevant records (kyc_results, screening_jobs, etc.), and emits audit events. |
| Step 4 — Error handling | If Edge Function processing fails, webhook_events row status = failed with error_message. A pg_cron job retries failed events up to 3 times with exponential backoff. Permanent failures alert via monitoring. |
| Idempotency | All webhook processing is idempotent. Provider webhook IDs are stored and duplicate detection prevents double-processing. Critical for screening providers that may retry on network error. |

SECTION 07

# Supabase and Vercel Implementation Plan

## 7.1 Supabase — Component Usage

| Supabase Component | Usage in This Project | Configuration Notes |
| --- | --- | --- |
| Postgres | Primary datastore for all structured data. All tables described in Section 3. | Enable pg_cron extension (periodic jobs). Enable pgcrypto (UUID generation, hash functions). Create application role with restricted permissions — no superuser. |
| Auth | User authentication, JWT with custom claims, session management, MFA. | Custom JWT hook: enrich JWT with tenant_id, role, permissions after sign-in. Hook implemented as Supabase Edge Function. Enable email verification. Enable TOTP MFA. |
| Storage | Document storage (passports, IDs, proof of address, certificates). | One bucket per tenant: documents-{tenant_id}. Bucket is private (no public access). RLS on storage.objects — users can only access their tenant's bucket. Max file size: 20MB. Allowed types: PDF, JPG, PNG, HEIC. |
| Edge Functions (Deno) | Webhook processing, async job handling, screening calls, audit event processing, scheduled jobs via pg_cron trigger, document hash computation. | Each module gets its own Edge Function file. Functions are stateless. Service role key stored in Edge Function secrets only — never in frontend env. |
| Realtime | Case queue updates — analysts see new cases appear in real-time without refresh. Case status changes push to open case views. | Supabase Realtime on cases table. Subscribe filtered by tenant_id and assigned_to. RLS applies to Realtime subscriptions. |
| Row Level Security | Tenant isolation, role-based read access, append-only enforcement on audit and event tables. | See Section 4.3 for full policy matrix. Enforce RLS on all tables including system tables. Test every policy with pgTAP. |
| Database Functions (RPC) | Complex multi-step operations that must be atomic: advance_workflow_step, record_approval_decision, resolve_screening_hit. Each operation writes multiple rows and audit events in a single transaction. | Functions run as SECURITY DEFINER where they need to bypass RLS for audit writes. Return typed JSONB responses. |

## 7.2 Vercel — Component Usage

| Vercel Feature | Usage | Configuration Notes |
| --- | --- | --- |
| Next.js App Router deployment | Primary application deployment. All pages and API routes. | Build command: next build. Node version: 20.x. Region: fra1 (Frankfurt) for EU compliance or iad1 (US East) — confirm data residency requirement before choosing. |
| Environment-based deployments | Production (main branch), Staging (staging branch), Preview (per PR). | Each environment has its own Supabase project. Preview environments use shared staging Supabase. Never share production env vars with preview. |
| Edge Middleware | Auth guard (check JWT before serving any authenticated page), tenant resolution from subdomain/path, redirect unauthenticated users, MFA check for sensitive routes. | Middleware runs at edge before any RSC or API route. Minimal logic only — read JWT claim, check tenant, redirect. No DB calls in middleware. |
| Vercel Cron Jobs | NOT used for compliance-critical operations. May be used for low-stakes tasks: sending summary emails, cache warming. | Compliance-critical jobs (re-screening, document expiry checks, periodic reviews) are driven by pg_cron + Supabase Edge Functions — not Vercel Cron. |
| Environment Variables | Supabase URL + anon key (public, safe for browser). All other keys (service role, screening provider API key, IDV secret) in Vercel env vars (server-only, never exposed to browser). | Use NEXT_PUBLIC_ prefix only for genuinely public config. All API keys are server-only. |
| ISR / Static Generation | Used for public-facing pages (marketing, login). All authenticated pages are dynamic (no caching of customer data). | Customer data pages: dynamic rendering only. No cache-control headers that could serve one user's data to another. |

SECTION 08

# Security and Compliance Implementation Checkpoints

These are engineering design decisions that must be made before coding, not retrofitted after. Each checkpoint has a concrete implementation requirement.

## 8.1 Encryption and Document Storage

| Documents at rest | Supabase Storage AES-256 encryption is applied by default. No additional implementation required for encryption at rest. DO NOT store documents in Postgres (as base64 or bytea) — always in Storage with metadata in the documents table. |
| --- | --- |
| Document hashing | When a document is uploaded, a Supabase Storage trigger fires an Edge Function that computes SHA-256 of the file content and stores it in documents.file_hash. This hash is the tamper-evidence mechanism for documents. |
| PII in database | Sensitive PII fields (full document number, tax ID, date of birth) should be encrypted at the application level using libsodium (available in Edge Functions / Deno) before write. The Supabase encryption column feature (pgsodium) can be used as an alternative for Postgres-native encryption. |
| Keys | [CONFIRM BEFORE BUILD] Supabase manages its own storage encryption keys. For application-level PII column encryption, a separate application secret key is required. Stored in Vercel env (server-only) and Supabase Edge Function secrets. Key rotation plan must be defined before go-live. |

## 8.2 Signed URL Access for Documents

| No direct URLs | All documents are stored in private Supabase Storage buckets. No public URLs exist. Any document access requires a freshly generated signed URL. |
| --- | --- |
| Signed URL TTL | 15-minute TTL for all signed download URLs. No exceptions. URL is generated per request from the API route — not cached or stored. |
| Access control before URL generation | The API route /api/documents/[id] performs: (1) auth check, (2) role check, (3) verify document.tenant_id matches user's tenant_id, (4) then call supabase.storage.from(bucket).createSignedUrl(). No signed URL is generated without all three checks passing. |
| Upload URLs | For uploads, a pre-signed upload URL is generated server-side and returned to the browser. The browser uploads directly to Supabase Storage — no document data passes through Vercel. The Vercel function only handles the URL generation request. |

## 8.3 PII Handling Rules

| No PII in logs | Application logs (Vercel log drain, Supabase logs) must contain zero PII. Log customer_id, session_id, case_id — never names, DOBs, document numbers, or email addresses in log strings. Implement a sanitise() utility that strips PII from error objects before logging. |
| --- | --- |
| No PII in URL parameters | Customer identifiers in URLs must use UUIDs (customer_id). Never include name, email, DOB, or document number in query strings or path parameters. |
| No PII in audit payload (raw) | Audit log payload stores field references and tokenised IDs. For field-change events, store field_name + old_value_hash + new_value_hash — not raw PII values. The actual value is in the customer_data_versions table with appropriate access controls. |
| Frontend state management | Customer PII fetched from API is never persisted to browser storage (localStorage, sessionStorage, IndexedDB, cookies). All PII exists only in React component state for the duration of the session. |
| Test and staging data | [CONFIRM BEFORE BUILD] Establish a synthetic data generation strategy before any production data flows through staging. Define the process for anonymising any production data used in testing. |

## 8.4 Audit and Event Logging Requirements

|  | Every engineering decision that changes data must emit an audit event. This is a development team norm, not an afterthought. During code review, any data mutation without a corresponding audit_log write is a blocking defect. |
| --- | --- |

| Where audit events are written | Primarily from Supabase Database Functions (RPC) that wrap multi-step transactions. Secondary: Supabase Edge Functions for async events. Never from API routes directly (risk of partial writes if audit fails after data write). |
| --- | --- |
| Audit write failure | If the audit write fails within a transaction, the entire transaction rolls back. Data integrity requires the audit record to exist. No silent audit failures. |
| What always gets audited | Every row insert/update on: customers, customer_data_versions, documents, cases, approvals, consent_records, screening_hit_resolutions, risk_assessments, workflow_definitions, tenant_config, user_roles. Use Postgres triggers for completeness. |
| Postgres triggers for audit | A generic audit trigger function (log_audit_event()) is created and attached to all compliance-critical tables. This ensures audit events are written even if a developer forgets to call the audit service in application code. |

## 8.5 Data Retention — Engineering Design Now

| Soft delete pattern | No hard deletes on any customer, document, case, or compliance record in MVP. deleted_at timestamp column on tables where deletion is eventually required. A scheduled Edge Function (pg_cron) handles eventual hard deletion of records past retention period. |
| --- | --- |
| Retention metadata on records | Each customer record stores: relationship_ended_at, retention_expires_at (computed from relationship_ended_at + configured retention period). The scheduled cleanup job queries retention_expires_at < now() AND deletion_approved = true. |
| Audit log — never deleted in MVP | Audit log has no deletion mechanism in MVP. Build the infrastructure (pg_cron job, deletion approval workflow) only when the first retention period expires in production. This is correct — the first records created today will not reach their retention expiry for 5+ years. |
| Document deletion | When a customer record passes retention period: delete from Supabase Storage, update documents.file_hash to "DELETED", update documents.storage_path to null. Metadata row is retained (document type, upload date, deletion date) as a compliance record of what was collected. |

SECTION 09

# Milestone-Based Build Plan

Six milestones cover the full MVP. Milestones are sequential — each is a dependency of the next. Each milestone produces a working, testable increment. Do not begin a milestone until the previous milestone's acceptance criteria are met.

| MILESTONE 1 · Foundation — Auth, RBAC, Audit, Tenant Setup |  |
| --- | --- |
| Objective | Establish the security and compliance backbone before any customer data flows. Auth, roles, RLS, audit trail, and tenant creation must be proven before onboarding is built. |
| Scope | — Supabase project setup (schema, extensions: pgcrypto, pg_cron, uuid-ossp) — tenants, users, user_roles, roles tables with RLS — Supabase Auth with custom JWT hook (tenant_id + role claims) — MFA setup flow for Admin and MLRO roles — audit_log table with append-only trigger (no UPDATE/DELETE) — Generic audit trigger function attached to all future compliance tables — Platform Super-Admin and Tenant Admin UI (user management, invite flow) — Vercel project setup: production + staging environments, env vars — Next.js project scaffold (App Router, Tailwind, shadcn/ui, Zod) — Edge Middleware: JWT validation, tenant resolution, auth guard — Role-based navigation shell (authenticated layout) |
| Outputs | — Working Supabase project with schema migrations (using Supabase migrations) — Auth flow: sign-in, email verify, MFA setup, sign-out — Tenant creation via platform admin — User invitation and role assignment — Audit log receiving events (can write manually to test) — Vercel: staging and production deployments live from repo |
| Dependencies | — Supabase project created with production + staging instances — Next.js repo initialised with folder structure per Section 10 — Vercel project connected to repo — Supabase migrations tooling set up (supabase CLI) |
| Acceptance Criteria | — Sign in as Tenant Admin → see dashboard, not another tenant's data — Sign in as Analyst → cannot access Admin config — Write a test audit event → cannot UPDATE or DELETE it — Invite a new user → user receives email, sets password, logs in with correct role — MFA required for Tenant Admin on second login — All RLS policies tested with pgTAP: at minimum one test per policy |

| MILESTONE 2 · Consent, Onboarding Session, Individual KYC Form |  |
| --- | --- |
| Objective | Implement the customer-facing onboarding journey for individual customers: consent capture, personal data collection, and document upload. |
| Scope | — consent_records table (append-only) + consent capture UI + API route — onboarding_sessions table + state machine (WorkflowEngine TypeScript class) — Default individual KYC workflow definition (JSON) loaded into workflow_definitions — Session initiation API + step submission API — Personal data collection form (M-02 fields per PRD Section 4.1.1) — customer table + customer_data_versions (append-only) — Document upload flow: signed upload URL generation → direct-to-Storage upload → document metadata record — document_events table (append-only) — Supabase Storage bucket setup (private, per-tenant, RLS) — Document hash computation Edge Function (triggered on Storage insert) — Customer-facing onboarding UI (multi-step form shell, progress indicator) — Field validation (Zod schemas matching PRD field requirements) |
| Outputs | — Working customer-facing onboarding journey: consent → personal data → document upload — Session state persisted: can resume an in-progress session — Documents stored in Supabase Storage with metadata in documents table and hash computed — consent_records written and immutable — All step submissions writing to customer_data_versions — All events writing to audit_log |
| Dependencies | — Milestone 1 complete (auth, RLS, audit) — IDV provider account created (Sumsub recommended) — even if not integrated yet, SDK and test credentials needed |
| Acceptance Criteria | — Submit consent form → consent_records row created, immutable — Complete personal data form → customer_data_versions row created with all required fields — Upload a passport → file appears in Supabase Storage, documents row created, file_hash populated — Interrupt session and return → session resumes at correct step — Attempt to DELETE a consent_record → Postgres error (permission denied) — All audit_log events present for each action above |

| MILESTONE 3 · IDV, Screening, Risk Scoring, and Case Management |  |
| --- | --- |
| Objective | Implement the automated compliance checks (KYC verification, sanctions screening, risk score) and the analyst review queue for cases that require human decision. |
| Scope | — IDV provider integration (Sumsub): initiate check → receive webhook → update kyc_results — Webhook receiver API route (/api/webhooks/idv) + Edge Function processor — webhook_events queue table for reliable webhook processing — Liveness + biometric match result parsing and storage in kyc_results (immutable) — Screening provider integration (ComplyAdvantage): submit job → receive webhook → create screening_hits — screening_jobs + screening_hits + screening_hit_resolutions tables — Screening webhook receiver + Edge Function processor — Risk scoring: 3-dimension implementation (customer, geo, product) → risk_assessments table (immutable) — Risk band routing logic in WorkflowEngine — cases table + case_events (append-only) — Analyst case queue UI: list, filter, sort by risk band and status — Case detail view: customer data, documents (signed URL), screening hits, risk score — Analyst actions: Add Note, Request Additional Information (RAI), Escalate, Approve, Reject — RAI notification: email sent to customer via Resend — approvals table + single-stage approval record — MLRO review queue (filtered view for MLRO role) |
| Outputs | — End-to-end flow working: consent → data → documents → IDV webhook → screening → risk score → case created → analyst reviews → decision recorded — All async jobs processed reliably via webhook_events queue — Case management UI functional for Analyst and MLRO roles — All decisions immutable in approvals table — All events in audit_log |
| Dependencies | — Milestone 2 complete — Screening provider account (ComplyAdvantage) with test API credentials — IDV provider webhook signing secret confirmed |
| Acceptance Criteria | — Submit a test onboarding → IDV webhook received → kyc_results populated — Run screening on a test customer → hits returned → analyst resolves hit → resolution immutable — Risk score computed → correct band assigned → case created for non-auto-approve — Analyst approves case → approval record written, immutable — MLRO logs in → sees only high-risk cases in their queue — Failed webhook (simulated network error) → retried by pg_cron job — All approvals visible in audit log with actor_id, role, timestamp |

| MILESTONE 4 · Admin Config UI and Tenant Workflow Management |  |
| --- | --- |
| Objective | Implement the tenant-facing admin configuration interface so tenants can manage their onboarding settings, user roles, workflow activation, and document requirements without code changes. |
| Scope | — tenant_config table (versioned JSONB) + admin config read/write API — Tenant Admin UI: module toggles, document type configuration, approval role selection — Workflow definitions management: view current version, view history, activate/deactivate (with MLRO acknowledgement) — User management UI: invite, assign role, deactivate (existing from M1 — extend with role editing) — Notification template editor (safe fields only: subject line, body copy — cannot disable mandatory notifications) — Branding settings: logo upload, company name — Risk band threshold display (read-only in MVP, shows current values) — Audit log viewer (MLRO/Admin role): filterable by entity, date range, event type — Tenant onboarding checklist: show which setup steps are complete before first customer can be processed |
| Outputs | — Tenant Admin can configure their instance without developer intervention — Workflow activation requires MLRO acknowledgement (checkbox + audit event) — All config changes versioned and visible in audit log — Audit log viewer functional for MLRO role |
| Dependencies | — Milestones 1–3 complete — At least one tenant fully onboarded end-to-end via Milestone 3 flow (proves the config being changed actually works) |
| Acceptance Criteria | — Tenant Admin changes document requirements → new workflow_definition version created → previous version preserved — Tenant Admin activates new workflow version without MLRO acknowledgement → blocked — MLRO acknowledges → activation proceeds → audit event written — Audit log viewer: query events for a specific customer → see complete chronological history — Tenant Admin changes branding → logo appears in customer-facing onboarding UI |

| MILESTONE 5 · Hardening, Error Handling, and Pre-Launch Compliance Review |  |
| --- | --- |
| Objective | Harden the MVP for production: error handling, edge cases, failed state recovery, PII audit of logs, load testing, and compliance review of the complete flow. |
| Scope | — Complete error boundary implementation across all UI — Retry logic for all external API calls (IDV, screening, email) — Graceful failure states: IDV unavailable → session paused, manual review triggered — PII audit: scan all log outputs for PII leakage (automated test) — All Zod validation schemas reviewed against PRD required fields — RLS policy test suite complete (pgTAP): every policy tested with correct and incorrect tenant contexts — Audit trail completeness test: run full onboarding flow and verify every step has audit event — Signed URL access test: verify document access denied without valid session — Load test: 50 concurrent onboarding sessions without degradation — Supabase connection pooling configured (PgBouncer mode) — Security review: no secrets in code, no PII in logs, no public Storage URLs — Data retention: soft-delete pattern verified, no hard deletes possible from application layer — MLRO walkthrough: MLRO completes a full high-risk case review and confirms flow is complete |
| Outputs | — Production-ready hardened application — Compliance sign-off from MLRO on the complete flow — Security checklist complete — All critical paths have automated tests |
| Dependencies | — Milestones 1–4 complete — MLRO available for walkthrough — Penetration test or security review scheduled (can be post-launch for MVP) |
| Acceptance Criteria | — All 10 onboarding scenarios (happy path, IDV fail, screening hit, high-risk, rejection, RAI) pass end-to-end — Zero PII in log output across any scenario — All RLS policies pass pgTAP test suite — MLRO confirms complete case management flow is operationally usable — Audit log export: produce a compliant audit report for a test customer |

| MILESTONE 6 · Production Deployment and Operational Readiness |  |
| --- | --- |
| Objective | Deploy to production with operational runbook, monitoring, and incident response procedures in place. |
| Scope | — Production Supabase project (separate from staging) with production data — Production Vercel project with production env vars — Monitoring: Vercel log drain + Sentry (error tracking) + Supabase dashboard alerts — pg_cron jobs activated: document expiry check (daily), failed webhook retry (hourly) — Supabase daily backup confirmed and restoration tested — Operational runbook: how to investigate a failed onboarding, how to manually retry a webhook, how to generate an audit report — First tenant fully onboarded to production (internal or pilot) — Domain + SSL confirmed — Incident response contact list |
| Outputs | — Live production environment — First real customer onboarded — Monitoring alerts confirmed working |
| Dependencies | — Milestone 5 complete — Production Supabase project paid plan (required for PITR and daily backups) — Production domain DNS configured |
| Acceptance Criteria | — Production deployment passes smoke test: full onboarding flow works on production — Sentry receives a test error and alert fires — pg_cron document expiry job runs successfully — Backup restoration test completed successfully — Monitoring dashboard active with key metrics: active sessions, case queue depth, webhook processing success rate |

SECTION 10

# Repository and Folder Structure

Monorepo structure. One repo, one Next.js app, one Supabase project per environment. Module boundaries enforced by directory. No barrel re-exports across module boundaries — explicit imports only.

|  | kyc-platform/ ├── .env.local # Local dev env vars (never committed) ├── .env.staging # Staging env vars (committed, no secrets) ├── next.config.ts ├── package.json ├── tsconfig.json ├── middleware.ts # Edge Middleware: auth guard, tenant resolution │ ├── supabase/ # Supabase CLI project │ ├── config.toml │ ├── migrations/ # All DB schema migrations (numbered) │ │ ├── 0001_create_tenants.sql │ │ ├── 0002_create_users_roles.sql │ │ ├── 0003_create_audit_log.sql │ │ ├── 0004_audit_triggers.sql │ │ ├── 0005_create_customers.sql │ │ ├── 0006_create_documents.sql │ │ ├── 0007_create_screening.sql │ │ ├── 0008_create_risk.sql │ │ ├── 0009_create_cases.sql │ │ ├── 0010_create_approvals.sql │ │ ├── 0011_create_consent.sql │ │ ├── 0012_create_sessions.sql │ │ ├── 0013_create_workflows.sql │ │ └── 0014_rls_policies.sql │ ├── functions/ # Supabase Edge Functions │ │ ├── process-idv-webhook/ │ │ │ └── index.ts │ │ ├── process-screening-webhook/ │ │ │ └── index.ts │ │ ├── compute-document-hash/ │ │ │ └── index.ts │ │ ├── enrich-jwt/ # Auth hook — add tenant_id + role to JWT │ │ │ └── index.ts │ │ ├── scheduled-document-expiry/ │ │ │ └── index.ts │ │ └── retry-failed-webhooks/ │ │ └── index.ts │ └── seed/ │ ├── roles.sql # Seed platform roles │ └── test-tenant.sql # Seed test tenant for dev │ ├── app/ # Next.js App Router │ ├── layout.tsx # Root layout │ ├── page.tsx # Public landing / redirect │ ├── (auth)/ # Auth routes (no tenant context required) │ │ ├── sign-in/ │ │ ├── sign-up/ │ │ └── mfa-setup/ │ ├── (onboarding)/ # Customer-facing onboarding (public + session auth) │ │ └── [tenantSlug]/ │ │ └── onboard/ │ │ ├── page.tsx # Session initiation │ │ ├── [sessionId]/ │ │ │ ├── consent/ │ │ │ ├── identity/ │ │ │ ├── documents/ │ │ │ └── complete/ │ ├── (platform)/ # Authenticated platform app │ │ ├── layout.tsx # Auth guard, tenant context provider │ │ ├── dashboard/ │ │ ├── cases/ │ │ │ ├── page.tsx # Case queue │ │ │ └── [caseId]/ │ │ │ └── page.tsx # Case detail │ │ ├── customers/ │ │ ├── audit/ │ │ └── admin/ │ │ ├── config/ │ │ ├── users/ │ │ └── workflows/ │ └── api/ # Route Handlers (API) │ ├── sessions/ │ ├── customers/ │ ├── documents/ │ ├── screening/ │ ├── risk/ │ ├── cases/ │ ├── approvals/ │ ├── consent/ │ ├── audit/ │ ├── admin/ │ └── webhooks/ │ ├── idv/ │ └── screening/ │ ├── modules/ # Business logic by bounded context │ ├── audit/ │ │ ├── audit.service.ts # emit(), query(), export() │ │ └── audit.types.ts │ ├── auth/ │ │ ├── auth.service.ts │ │ ├── rbac.ts # Permission checks, role definitions │ │ └── auth.types.ts │ ├── onboarding/ │ │ ├── engine.ts # WorkflowEngine class │ │ ├── onboarding.service.ts │ │ ├── session.repository.ts │ │ └── onboarding.types.ts │ ├── kyc-individual/ │ │ ├── kyc.service.ts │ │ ├── kyc.repository.ts │ │ └── kyc.types.ts │ ├── documents/ │ │ ├── documents.service.ts # upload URL generation, metadata, hash │ │ ├── documents.repository.ts │ │ └── documents.types.ts │ ├── screening/ │ │ ├── screening.service.ts │ │ ├── screening.repository.ts │ │ ├── adapters/ │ │ │ ├── ScreeningAdapter.ts # Interface │ │ │ ├── ComplyAdvantageAdapter.ts │ │ │ └── MockScreeningAdapter.ts │ │ └── screening.types.ts │ ├── risk/ │ │ ├── risk.service.ts # compute(), getLatest(), getDimensions() │ │ ├── risk.repository.ts │ │ ├── dimensions/ # One file per risk dimension │ │ │ ├── customer.dimension.ts │ │ │ ├── geographic.dimension.ts │ │ │ └── product.dimension.ts │ │ └── risk.types.ts │ ├── cases/ │ │ ├── cases.service.ts │ │ ├── cases.repository.ts │ │ └── cases.types.ts │ ├── approvals/ │ │ ├── approvals.service.ts │ │ ├── approvals.repository.ts │ │ └── approvals.types.ts │ ├── consent/ │ │ ├── consent.service.ts │ │ ├── consent.repository.ts │ │ └── consent.types.ts │ ├── notifications/ │ │ ├── notifications.service.ts │ │ ├── adapters/ │ │ │ ├── NotificationAdapter.ts │ │ │ ├── ResendAdapter.ts │ │ │ └── MockNotificationAdapter.ts │ │ └── notifications.types.ts │ └── admin-config/ │ ├── config.service.ts │ ├── workflow.service.ts │ └── config.types.ts │ ├── lib/ # Shared utilities (no business logic) │ ├── supabase/ │ │ ├── client.ts # Browser Supabase client │ │ ├── server.ts # Server Supabase client (cookies) │ │ └── admin.ts # Service role client (Edge Functions only) │ ├── validations/ # Zod schemas (shared between client and server) │ ├── errors/ # Error types and error handling utilities │ ├── crypto/ # Hash functions, token generation │ └── constants/ # Enums: roles, risk bands, event types, status codes │ ├── components/ # UI components │ ├── ui/ # shadcn/ui base components │ ├── onboarding/ # Customer onboarding UI components │ ├── cases/ # Case management UI components │ ├── admin/ # Admin config UI components │ └── shared/ # Shared layout, navigation, auth UI │ └── tests/ ├── unit/ # Unit tests per module ├── integration/ # API route integration tests ├── e2e/ # Playwright end-to-end tests (key flows) └── db/ # pgTAP SQL tests for RLS policies |
| --- | --- |

SECTION 11

# Risks and Open Questions

## 11.1 Architecture Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Vercel function timeout on synchronous IDV / screening calls | High | High | Async webhook architecture (Section 6.4) eliminates this. Do not attempt synchronous third-party calls in Vercel functions. Confirmed in architecture before build starts. |
| Supabase RLS performance at scale (complex policies + JOIN-heavy queries) | Medium | Medium | Index tenant_id on every table. Test with realistic data volumes before Phase 2 scale. Add materialised view for case queue if needed. |
| JWT custom claims hook reliability (auth enrichment) | Medium | High | Test auth hook failure modes. Implement fallback: if claims missing, force re-authentication. Monitor hook invocation errors in Supabase logs. |
| Edge Function cold start for critical webhook processing | Low | Medium | Supabase Edge Functions are Deno-based with lower cold start than Node. webhook_events queue means a cold start delays processing but does not drop events. Acceptable for MVP. |
| Schema migration management across environments | Medium | High | Use Supabase CLI migrations exclusively. Never apply manual SQL to production. Each PR includes migration file. Migration applied to staging before production. |

## 11.2 Compliance and Regulatory Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Simplified Due Diligence activated without legal sign-off | Medium | High | SDD is disabled in MVP by default. Can only be activated by Tenant Admin + MLRO acknowledgement. Legal sign-off requirement documented in admin UI. |
| Biometric data classification triggering stricter local requirements | Medium | High | [CONFIRM BEFORE BUILD] UAE PDPL Art. 4 classifies biometric data as sensitive. Confirm with data protection counsel that Sumsub's data handling (where biometric is processed/stored) satisfies UAE PDPL requirements. |
| Tipping-off via system messages | Low | High | Case rejection notifications are reviewed against tipping-off rules before template is finalised. SAR-related case status never shown to non-MLRO roles in UI. Confirm notification templates with MLRO before go-live. |
| Screening list coverage — UAE Executive Office list not in default provider config | Medium | High | [CONFIRM BEFORE BUILD] UAE Executive Office for Control and Non-Proliferation list is mandatory for UAE-licensed entities. Confirm ComplyAdvantage coverage or add supplementary screening source. |
| Cross-border data transfer to IDV provider | Medium | Medium | [CONFIRM BEFORE BUILD] Confirm Sumsub's data residency options for UAE customer data. If Sumsub processes data outside UAE, document the legal basis for transfer (explicit consent captured at onboarding). |

## 11.3 Integration Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| IDV provider webhook delivery failure (missed events) | Low | High | webhook_events queue + retry pg_cron job. Idempotent processing. Monitor for stuck pending events. Provider retry should overlap with internal retry. |
| Screening provider API rate limits during bulk re-screening | Medium | Medium | Phase 2 concern. MVP screening is per-customer at onboarding only. Rate limiting strategy for batch screening deferred to Phase 2. |
| ComplyAdvantage PEP/sanctions data freshness | Low | Medium | Store list version at time of screening. Periodic re-screening in Phase 2 ensures stale results are refreshed. Acceptable risk for MVP. |
| Resend email deliverability to .ae domains and UAE ISPs | Low | Medium | Test with real UAE email addresses before go-live. Configure SPF, DKIM, DMARC on sending domain. Monitor delivery rates from day one. |

## 11.4 Delivery Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Scope creep: pressure to build KYB / EDD before MVP is stable | High | High | MVP scope is fixed (Section 1.1). Any addition is a formal scope change decision. The milestone acceptance criteria are the scope gate. |
| IDV provider integration complexity exceeding estimate | Medium | Medium | Sumsub has well-documented Next.js integration. Start with Sumsub SDK web integration. Allocate 3-5 days for integration including webhook testing. |
| Supabase Auth custom hook complexity | Medium | Medium | Prototype JWT enrichment hook in Milestone 1 before building anything that depends on role claims. This is the riskiest infrastructure dependency. |
| Claude Code context management across long sessions | Medium | Low | Structure each Claude Code session around a single module. Provide the repo structure and module files as context. Never ask Claude Code to build across multiple modules in one session. |

## 11.5 Assumptions Requiring Confirmation Before Build

[CONFIRM BEFORE BUILD] — These must be resolved before coding the affected component.

| Assumption | Resolution Needed | Blocks |
| --- | --- | --- |
| Sumsub is the selected IDV provider | Confirm provider selection. Account creation and API credentials required before Milestone 3. | Milestone 3 (IDV integration) |
| ComplyAdvantage is the selected screening provider | Confirm account setup. API key and webhook secret required before Milestone 3. | Milestone 3 (Screening integration) |
| Resend is the selected email notification provider | Confirm account. Domain DNS (SPF, DKIM) setup required. | Milestone 3 (RAI notifications) |
| UAE data residency: Vercel region = fra1 or me-1 (Middle East)? | Vercel has a Middle East region (me-1, Bahrain). If UAE data residency is a client requirement, me-1 must be selected. Confirm before Vercel project creation. | Milestone 1 (Vercel project setup) |
| Sumsub's UAE/GCC data processing satisfies UAE PDPL | Legal counsel to confirm or DPA with Sumsub to be executed. Cross-border transfer consent captured in onboarding consent form. | Milestone 2 (Consent form design), Milestone 3 (IDV integration) |
| Single Supabase project (shared schema + RLS) is acceptable for MVP | Confirmed as [ASSUMPTION] in Section 3.1. If a tenant requires dedicated schema, this is a Phase 2 migration. Confirm pilot tenant requirements. | Milestone 1 (database schema design) |
| MLRO is available for Milestone 5 walkthrough | MLRO must walk through the complete high-risk case flow in Milestone 5. If MLRO is not yet appointed, Milestone 5 cannot be completed. | Milestone 5 (compliance sign-off) |
| UAE Executive Office list is covered by ComplyAdvantage | Confirm with ComplyAdvantage that UAE Executive Office for Control and Non-Proliferation list is included in the data package. If not, identify supplementary source. | Milestone 3 (Screening completeness) |

TruVis International Services

Where Trust Creates True Vision

KYC / AML Platform — Development Plan v1.0 — 2026

Confidential and Proprietary